## Interfaces
InterfaceID | Name | Direction | Protocol | Partner | Country | Status | Owner | Notes
IF-001 | React → Tryton JSON-RPC | Outbound | JSON-RPC/HTTPS | GNU Health | Both | Live | Engineering | Primary app API
IF-002 | SAO → Tryton | Outbound | JSON-RPC/HTTPS | GNU Health | Both | Live | Engineering | Admin/wizards
IF-003 | NABIDH ADT/ORU/etc. | Outbound | HL7v2 | DHA | UAE-DXB | Planned | Integration | Needs confirmation
IF-004 | NABIDH C-CDA | Outbound | C-CDA | DHA | UAE-DXB | Planned | Integration | Needs confirmation
IF-005 | Malaffi clinical exchange | Bidirectional | TBD | DoH | UAE-AUH | Planned | Integration | Confirm specs
IF-006 | Riayati HIE | Bidirectional | HL7/FHIR/IHE | MOHAP | UAE | Planned | Integration | Confirm profiles
IF-007 | Qatar national e-health | Bidirectional | TBD | MoPH | QA | Unknown | Compliance | Confirm existence/mandate
IF-008 | Orthanc PACS | Bidirectional | DICOM | Internal | Both | Optional | Imaging | health_orthanc
IF-009 | Claims / eClaim | Outbound | TBD | Payer/regulator | UAE | Not started | Billing | Needs confirmation
IF-010 | SMTP / notifications | Outbound | SMTP | Email gateway | Both | Not started | Ops | No PHI in subject lines