## Traceability
ReqID | Requirement | Country | Authority | OfficialSource | SourceDate | Classification | GHModule | SupportLevel | Gap | Action | Owner | Status
REQ-UAE-001 | HIE connectivity for Dubai facilities (NABIDH) | UAE | DHA | NABIDH Interoperability Standards PDF | 2022-10 | Needs legal confirmation | None | Unsupported | No HL7/FHIR gateway | Engage DHA; design interface service | Compliance | Open
REQ-UAE-002 | Support HL7 v2 for HIE submission | UAE | DHA/MOHAP | NABIDH + Riayati standards | 2022 | Recommended (published standards) | None | Unsupported | No message engine | Implement adapter | Integration | Open
REQ-UAE-003 | Support FHIR APIs where required by HIE | UAE | DHA/MOHAP | Riayati Terminology & Coding Standards v2.1 | 2022-06-29 | Recommended | None | Unsupported | No FHIR server/client | FHIR gateway design | Integration | Open
REQ-UAE-004 | C-CDA clinical document exchange | UAE | DHA | NABIDH implementation guidelines | n/a | Needs legal confirmation | None | Unsupported | No C-CDA export | Map clinical docs | Integration | Open
REQ-UAE-005 | IHE profiles (XDS/PDQ/etc.) as applicable | UAE | MOHAP/DHA | Riayati standards | 2022 | Needs legal confirmation | None | Unsupported | No IHE actors | Confirm required profiles | Compliance | Open
REQ-UAE-006 | Malaffi participation (Abu Dhabi) | UAE | DoH | Malaffi program communications | 2023+ | Needs legal confirmation | None | Unsupported | No connector | Facility onboarding if in scope | Compliance | Open
REQ-UAE-007 | Riayati / NUMR alignment | UAE | MOHAP | MOHAP announcement + Riayati tech docs | 2023+ | Needs legal confirmation | None | Unsupported | No connector | Confirm facility obligations | Compliance | Open
REQ-UAE-008 | UAE PDPL controls for health/sensitive data | UAE | Federal PDPL | Federal Decree-Law No. 45/2021 (confirm text) |  | Needs legal confirmation | health_crypto (partial) | Partial | No DPIA/process pack | Counsel + DPIA | Legal | Open
REQ-UAE-009 | Coding standards (ICD/LOINC/SNOMED as specified) | UAE | MOHAP/DHA | Riayati coding standards | 2022 | Needs legal confirmation | health_icd10/11 | Partial | SNOMED/LOINC licensing unknown | Confirm licenses & maps | Clinical Informatics | Open
REQ-QA-001 | MoPH facility HIS / e-health obligations | Qatar | MoPH | moph.gov.qa — specific mandate TBD |  | Needs legal confirmation | health* | Partial | Mandate set not confirmed | Formal MoPH inquiry | Compliance | Open
REQ-QA-002 | PDPPL special-nature health data processing | Qatar | NDPO/NCSA | Law No. 13 of 2016 | 2016/2017 | Needs legal confirmation | N/A | Partial | Permits/DPIA not implemented in product | Counsel + technical controls | Legal | Open
REQ-QA-003 | Patient consent & access controls | Qatar | MoPH/NDPO | PDPPL + MoPH patient rights (confirm) |  | Needs legal confirmation | res.group / record rules | Partial | No consent registry UI | Design consent module | Product | Open
REQ-BOTH-001 | Audit trail for PHI access | UAE/QA | Privacy authorities | PDPL/PDPPL principles (confirm) |  | Recommended / confirm mandatory | Tryton model history | Partial | No privacy-centric audit UI | Enhance logging | Security | Open
REQ-BOTH-002 | Tenant isolation multi-country | UAE/QA | Governance | Internal policy | 2026-07-14 | Recommended | company.company | Partial | Single demo company | Org hierarchy + rules | Architecture | In progress
REQ-BOTH-003 | No real PII in non-prod | UAE/QA | Internal | IST policy | 2026-07-14 | Mandatory (internal) | synthetic_data | Supported | Need production gate | Refuse prod import without override | Engineering | In progress
REQ-INT-001 | HL7 trademark / FHIR use compliance | Intl | HL7 | hl7.org IP policy |  | Recommended | N/A | N/A | Docs only | Follow IP policy | Legal | Open
REQ-INT-002 | SNOMED CT affiliate license if used | Intl/UAE/QA | SNOMED Int'l | snomed.org |  | Needs legal confirmation | None verified | Unsupported | License unknown | Confirm national membership | Clinical Informatics | Open
REQ-INT-003 | LOINC attribution license | Intl | Regenstrief | loinc.org/license |  | Recommended if used | None verified | Unsupported | Not loaded | Adopt with attribution | Clinical Informatics | Open
REQ-INT-004 | ICD commercial redistribution rules | Intl | WHO | WHO classifications |  | Needs legal confirmation | health_icd* | Partial | National license unclear | Confirm with focal point | Legal | Open
REQ-INT-005 | DICOM if imaging/PACS integrated | Intl | NEMA | dicomstandard.org |  | Recommended if imaging | health_imaging / orthanc | Partial | Not wired in React | Optional Orthanc | Imaging | Open

## Legend
Classification | Meaning
Mandatory | Confirmed legal/regulatory obligation — only after authority confirmation
Recommended | Published standard or best practice; confirm applicability
Needs legal confirmation | Do not treat as binding until counsel/authority confirms
Internal | IST project policy