## Controls
ControlID | Domain | Control | UAERef | QatarRef | Implementation | Status | Evidence | ResidualRisk
CTL-01 | Access | Unique user accounts | PDPL principles — confirm | PDPPL — confirm | res.user | Partial | UsersPage | Shared accounts possible
CTL-02 | Access | Role-based groups | Confirm | Confirm | res.group + ir.model.access | Partial | GroupsPage | No IST role pack yet
CTL-03 | Access | Session security | Confirm | Confirm | Tryton Session; localStorage MVP | Gap | ARCHITECTURE.md | Move to httpOnly/JWT
CTL-04 | Data | Encryption in transit | Confirm | Confirm | HTTPS nginx | Partial | HTTPS.md | Confirm TLS config
CTL-05 | Data | Encryption at rest | Confirm | Confirm | GCP disk — verify | Needs verification | VM | Enable CMEK if required
CTL-06 | Privacy | Synthetic-only non-prod | Internal | Internal | synthetic markers + import gate | In progress | synthetic factory
CTL-07 | Privacy | No real national IDs in demos | Internal | Internal | SYN-QA-/SYN-AE- formats | Implemented in templates | Master data
CTL-08 | Audit | Access logging | Confirm | Confirm | Tryton + nginx logs | Partial | VM logs | Central SIEM TBD
CTL-09 | Tenancy | Country/entity isolation | Governance | Governance | company + record rules TBD | Gap | gap-analysis | Cross-border leakage
CTL-10 | Integrity | Backup & restore | Confirm | Confirm | PostgreSQL backups TBD | Needs verification | Ops | Document RPO/RTO
CTL-11 | Interop | Secure HIE channels | NABIDH/Riayati | MoPH TBD | Not implemented | Gap | interface-register | No production HIE
CTL-12 | Vendor | No GH upgrade without CAB | Internal | Internal | Policy | Policy | implementation guide