## P0 Parity
Screen ID | Menu path | SAO available | React route | Status | Priority | Compare notes | Build next action | Owner | Updated
P0-LOGIN | Auth / Login | Y | /login | Partial | P0 | IST login works; SAO has own login if session missing in iframe | Share session / SSO note; document dual login | Frontend | 2026-07-15
P0-DASH | Health / Dashboard | Y | / | Partial | P0 | React dashboard cards; SAO home richer | Align KPIs with demo script | Frontend | 2026-07-15
P0-CO | Administration / Companies | Y | /companies | Partial | P0 | List/create OK; deep CoA link via Workspace | Harden multi-company switch UX | Frontend | 2026-07-15
P0-CUR | Financial / Currency | Y | /currency | Partial | P0 | List AED/QAR; rates in SAO | Confirm rates UX if needed | Frontend | 2026-07-15
P0-PARTY | Party / Parties | Y | /parties | Partial | P0 | List/basic; deep tabs SAO | Party categories/address depth | Frontend | 2026-07-15
P0-PAT | Health / Patients | Y | /patients | Partial | P0 | List + detail; insurance/family SAO | Deep demographics Hybrid | Frontend | 2026-07-15
P0-APT | Health / Appointments | Y | /appointments | Partial | P0 | Create/list; specialty links Hybrid | Product/insurance linking | Frontend | 2026-07-15
P0-LAB | Health / Laboratory | Y | /laboratory | Stub | P0 | Orders list; create-test/results SAO | Workspace CTA + result view later | Frontend | 2026-07-15
P0-RX | Health / Prescriptions | Y | /medications;/pharmacy | Stub | P0 | Lists; create/dispense wizards SAO | Rx create + stock-move Hybrid | Frontend | 2026-07-15
P0-EVAL | Health / Evaluations | Y | /evaluations | Stub | P0 | List/create thin; full form SAO | Harden consultation form | Frontend | 2026-07-15
P0-BED | Health / Beds / Inpatient | Y | /beds | Stub | P0 | Bed board thin; admit/transfer SAO | Admit/discharge basics | Frontend | 2026-07-15
P0-FIN | Financial / Invoices | Y | /financial | Stub | P0 | List + draft stub; post/pay SAO | Guided Workspace for CoA/post | Frontend | 2026-07-15
P0-USR | Administration / Users | Y | /users | Partial | P0 | CRUD light; ACL depth SAO | Groups permissions summary | Frontend | 2026-07-15
P0-SETUP | IST / Setup Hub | N* | /setup | Partial | P0 | IST-only hub; SAO for wizards | Keep; link Workspace | Frontend | 2026-07-15
P0-HELP | IST / Help Centre | N* | /help | Partial | P0 | React Help; screenshots backlog | Screenshot pack | Docs | 2026-07-15
P0-WS | IST / Workspace (SAO embed) | Y | /workspace | Partial | P0 | Embed live; theming via custom.css | Optional ?path= deep-link | Frontend | 2026-07-15
P0-STAFF | Health / Health Professionals | Y | /staff | Partial | P0 | List/detail; specialty O2M SAO | Specialty linking | Frontend | 2026-07-15
P0-IMG | Health / Imaging | Y | /imaging | Stub | P0 | List; generate-result/Orthanc SAO | Workspace CTA | Frontend | 2026-07-15
P0-NUR | Health / Nursing | Y | /nursing | Stub | P0 | List; rounding/stock SAO | Document Hybrid | Frontend | 2026-07-15
P0-PROC | Health / Procedures | Y | /procedures | Stub | P0 | List thin | Workspace for deep form | Frontend | 2026-07-15
P0-PROD | Product / Products | Y | /products | Partial | P0 | Catalog list; UoM/accounts SAO | Account categories after CoA | Frontend | 2026-07-15
P0-STK | Stock / Inventory | Y | /stock | Partial | P0 | Locations/moves list; wizards SAO | Adjustment wizards Workspace | Frontend | 2026-07-15
P0-CAL | Calendar | Y | /calendar | Stub | P0 | Thin; events often SAO | Optional if module empty | Frontend | 2026-07-15
P0-MOD | Administration / Modules | Y | /modules | Stub | P0 | Mark-only; apply = SAO/admin | Keep Workspace + trytond-admin | Ops | 2026-07-15
P0-GRP | Administration / Groups | Y | /groups | Stub | P0 | List; ACL matrix SAO | Summary view | Frontend | 2026-07-15
P0-SEQ | Administration / Sequences | Y | /sequences | Partial | P0 | List/edit light | Confirm numbering per company | Frontend | 2026-07-15
P0-CTR | Administration / Countries | Y | /countries | Partial | P0 | Read/list | Rarely change | Frontend | 2026-07-15
P0-LANG | Administration / Languages | Y | /languages | Partial | P0 | Read/list | Rarely change | Frontend | 2026-07-15
P0-SET | IST / Settings | N* | /settings | Partial | P0 | Client settings + SAO URL | Point to Workspace | Frontend | 2026-07-15
P0-MENU | Menus / Model browser | Y | /menu/:id | Partial | P0 | Generic act_window; wizards to Workspace | Extend model coverage | Frontend | 2026-07-15